## Sayfa1
SCHEDULE OF INSTITUTE AUTOMATION SYSTEM (IAS) - CSE490
TASK # | TASK ID | TASK TITLE | TASK DEFINITION | START DATE | END DATE (EXPECTED)
1 | IAS001 | Boostrap Template | To find Boostrap template and apply into the system | 2018-04-13 | 2018-04-13
2 | IAS002 | Display #1 | To implement display defs of institute part | 2018-04-14 | 2018-04-15
3 | IAS003 | Display #2 | To implement display defs of academic staff part | 2018-04-15 | 2018-04-15
4 | IAS004 | Display #3 | To implement display defs of institute staff part | 2018-04-15 | 2018-04-15
5 | IAS005 | Display #4 | To implement display defs of grand student part | 2018-04-15 | 2018-04-15
6 | IAS006 | Def #1 | To implement the defs : accept, reject, withdraw | 2018-04-16 | 2018-04-16
7 | IAS007 | Def #2 | To implement the defs : define-delete course, open-close section | 2018-04-17 | 2018-04-17
8 | IAS008 | RAD | To write new document (volume 2) | 2018-04-15 | 2018-04-20
9 | IAS009 | SDD | To start to make the document | 2018-04-20 | 2018-04-21
10 | IAS010 | Test | Testing of completely system
11 | IAS011 | Review | Documentation Review
12 | IAS012 | V&V | Validation and verification of the system
13 | IAS013 | Full Implementation | To edit UX
14 | IAS014
15 | IAS015
16 | IAS016
17 | IAS017
18 | IAS018
19 | IAS019
20 | IAS020